## Week
| EXP (Photo_ATB) |  | Diagramme de gant pour la phase 2 (= Second semestre)
|  |  | Semaine de départ | 2022-02-12
| Semaine | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Personnes Concernées | date | 2022-02-12 | 2022-02-19 | 2022-02-26 | 2022-03-05 | 2022-03-12 | 2022-03-19 | 2022-03-26 | 2022-04-02 | 2022-04-09 | 2022-04-16 | 2022-04-23 | 2022-04-30 | 2022-05-07 | 2022-05-14 | 2022-05-21 | 2022-05-28 | 2022-06-04 | 2022-06-11 | 2022-06-18 | 2022-06-25 | Etat d'avancement
|  | 2022-02-12 | 2022-02-19 | 2022-02-26 | 2022-03-05 | 2022-03-12 | 2022-03-19 | 2022-03-26 | 2022-04-02 | 2022-04-09 | 2022-04-16 | 2022-04-23 | 2022-04-30 | 2022-05-07 | 2022-05-14 | 2022-05-21 | 2022-05-28 | 2022-06-04 | 2022-06-11 | 2022-06-18 | 2022-06-25
Jean-Batptiste | Algorithmes P3 | [20 empty] | En cours | bar: 2022-04-09 to 2022-05-21
Selyan,Mael | Faire le SW | [20 empty] | En cours | bar: 2022-03-12 to 2022-05-07
Nicolas,Mael | Création de la BDD | [20 empty] | Fini | bar: 2022-04-23 to 2022-04-30
Jean-Baptiste, Nicolas,Mael | Algorithmes PUI | [20 empty] | En cours | bar: 2022-03-12 to 2022-05-21
Mael | SS du SW | [20 empty] | En cours | bar: 2022-04-30 to 2022-05-21
Jean-Baptiste, Nicolas | réalisation du TEST | bar: 2022-05-28 to 2022-06-04
P

## Sample
Project Title | [20 empty] | Project Schedule
|  | Start Week | 2021-10-20
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Starting | 2021-10-20 | 2021-10-27 | 2021-11-03 | 2021-11-10 | 2021-11-17 | 2021-11-24 | 2021-12-01 | 2021-12-08 | 2021-12-15 | 2021-12-22 | 2021-12-29 | 2022-01-05 | 2022-01-12 | 2022-01-19 | 2022-01-26 | 2022-02-02 | 2022-02-09 | 2022-02-16 | 2022-02-23 | 2022-03-02 | Notes
| 2021-10-20 | 2021-10-27 | 2021-11-03 | 2021-11-10 | 2021-11-17 | 2021-11-24 | 2021-12-01 | 2021-12-08 | 2021-12-15 | 2021-12-22 | 2021-12-29 | 2022-01-05 | 2022-01-12 | 2022-01-19 | 2022-01-26 | 2022-02-02 | 2022-02-09 | 2022-02-16 | 2022-02-23 | 2022-03-02
Phase | 2022-03-02: P R O J E C T E N D
One | 2021-10-27: Project Plan
Plan Review
Phase | 2021-11-10: Draft Requrements
Two | 2021-11-10: Capacity Planning
Project Test Plan
Acceptance Test Plan
Final Requirements Specifications
Phase Review and Approval
Phase | 2021-12-01: Milestone: additional funds; 2021-12-08: Draft Design Specifications
Three | 2021-12-08: Configuration Management Plan
Architectue Design Plan
Define Interface Requirements
Shared Component Design
Integration Test Plan
Define Project Guidelines
Final Design Specifications
Phase Review and Approval